## Schedule - EXAM26
Revised Housing Trajectory for Matter 12 hearing session EXAM/26
Site reference | Status | Parish | Ward | Allocation reference in new Local Plan to 2036 | Name and address of site | Approx site area gross (ha) | Approx site area net (ha) | Notes | Available | Suitable | Achievable | Total no of dwellings already built on site | Total residual no of dwellings under construction, permitted/ allocated/ potential capacity to 2036 | Total no. of dwellings on site by 2036 | Number of residual expected to be completed in 5 years | 2017/18 | Actual Completions 2017/18 | Under Construction 2017/18 | 2018/19 Yr 1 | 2019/20 Yr 2 | 2020/21 Yr 3 | 2021/22 Yr 4 | 2022/23 Yr 5 | 2023/24 Yr 6 | 2024/25 Yr 7 | 2025/26 Yr 8 | 2026/27 Yr 9 | 2027/28 Yr 10 | 2028/29 Yr 11 | 2029/30 Yr 12 | 2030/31 Yr 13 | 2031/32 Yr 14 | 2032/33 Yr 15 | 2033/34 Yr 16 | 2034/35 Yr 17 | 2035/36 Yr 18 | Total 2018-2036
Existing Planning Permissions - Unallocated sites and 2002 Local Plan Allocations & Huntingdon West AAP
15/00079/FUL | Full | Holme | Stilton |  | Land Adjacent 25 St Giles Close, Holme | 0.3 | 0.2 | Completions 17/18 exceeded trajectory by 8 balance remaining of 0 for 18/19. Part brownfield. Agent says site is under construction and due for completion summer 2018. | Yes | Yes | Yes | 8 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1300679FUL | Full | Brington & Molesworth | Ellington |  | Hill Rise & Hill Close, Brington | 5.4 | 4.5 | 17/18 completions exceeded trajectory by 2 so 18/19 projection reduced by 2. Brownfield. 56 new dwellings following demolition of 40 existing former MOD dwellings so only actually 16 net additional dwellings (40 lost, 24 already built and 32 outstanding). | Yes | Yes | Yes | 43 | 13 | 56 | 13 | 17 | 19 | 9 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
1301798FUL | Full | Godmanchester | Godmanchester |  | 3-5 Bridge Place, Godmanchester | 0.02 | 0.02 | Brownfield. Under construction. Conservation issues have delayed progress somewhat, but the site is anticipated for completion within 2/3 years. | Yes | Yes | Yes | 0 | 12 | 12 | 12 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
15/00016/FUL | Full | St Neots | St Neots Eaton Ford |  | Eaton Gate (Eaton Court), Great North Road, Eaton Ford | 1.25 | 1.2 | Brownfield. Site progressing well and approaching completion. | Yes | Yes | Yes | 29 | 0 | 29 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/00029/FUL | Full | Bury | Warboys And Bury |  | Former Clinic RAF Upwood | 2.4 | 2 | Brownfield. Agent says site has been cleared ready for development. Agent's projections deferred by one year as appear optimistic given development has not yet commenced. | Yes | Yes | Yes | 0 | 60 | 60 | 60 | 0 | 0 | 0 | 10 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
15/00659/FUL | Full | Yaxley | Yaxley And Farcet |  | Former Ashton House, Yaxley | 0.3 | 0.29 | Brownfield. Site approaching completion. | Yes | Yes | Yes | 12 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/00570/FUL | Full | Colne | Somersham |  | S. of The Rhees, Bluntisham Rd, Colne | 1.6 | 1.4 | 18/19 trajectory increased by 10 to account for under delivery in 17/18. Greenfield. Rural exceptions site for 10 affordable and 2 open market dwellings. Site progressing well. | Yes | Yes | Yes | 0 | 12 | 12 | 12 | 10 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
16/02011/FUL | Full | St Ives | St Ives South |  | 7 - 8 New Road, St Ives | 0.1 | 0.1 | Brownfield. Agent says site can be developed within 5 years. | Yes | Yes | Yes | 0 | 11 | 11 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
16/01912/FUL | Full | Offord Cluny And Offord Darcy | Gransden And The Offords |  | Land At Paxton Road Farm, Paxton Rd, Offord D'Arcy | 0.7 | 0.6 | Greenfield. Approved October 17. Applicant intends to commence on site in Jan 18. | Yes | Yes | Yes | 0 | 20 | 20 | 20 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
0700364REM | Reserved Matters | Sawtry | Sawtry |  | The Old Granary, Gidding Rd | 0.6 | 0.6 | Brownfield. Rough foundations in place so material start has been implemented. Developer says site could be completed by 2019. | Yes | Yes | Yes | 0 | 10 | 10 | 10 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
0200293REM | Reserved Matters | Sibson cum Stibbington | Elton And Folksworth |  | Waters Edge, Ship End Quarry, Wansford | 9.3 | 2.3 | 18/19 trajectory increased by 4 to account for under delivery in 17/18. Brownfield. Estimated based on officer knowledge of progress on site. | Yes | Yes | Yes | 22 | 5 | 27 | 5 | 4 | 0 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
1402198REM | Reserved Matters | Yaxley | Yaxley And Farcet |  | New Horizons (Former Snowcap Mushrooms) Mere View, Yaxley | 2.3 | 1.8 | 17/18 completions exceeded trajectory by 5 so 18/19 projection reduced by 5 to zero as site is complete.Brownfield. Site progressing well. Developer says site will be completed in 2018/19. | Yes | Yes | Yes | 78 | 0 | 78 | 0 | 48 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01711/REM | Reserved Matters | Fenstanton | Fenstanton |  | The Orchard (Former Ivy Nursery), Fenstanton | 1.5 | 0.8 | Mainly greenfield. Site completed. | Yes | Yes | Yes | 35 | 0 | 35 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01817/REM | Reserved Matters | Warboys | Warboys And Bury |  | Great Pastures, West of Station Rd, Warboys | 5 | 3.3 | Completions 17/18 exceeded trajectory by 1 therefore balance for 18/19 reduced by 1. Greenfield. Site is progressing well. | Yes | Yes | Yes | 72 | 48 | 120 | 48 | 65 | 66 | 35 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
0704012S73 | Reserved Matters | St Neots | St Neots Priory Park |  | Loves Farm, St Neots | 63.2 | 30.5 | Greenfield. Multiple developers. Site approaching completion. | Yes | Yes | Yes | 1438 | 0 | 1438 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01423/FUL | Full | Huntingdon | Huntingdon West |  | Ermine St/Edison Bell Way | 0.3 | 0.3 | Brownfield. Part of residue of HW4 in HWAAP (for committed sites on HW4 see above). Site completed autumn 2017. | Yes | Yes | Yes | 47 | 0 | 47 | 0 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16/00337/REM | Reserved Matters | Huntingdon | Huntingdon West |  | South of Edison Bell Way | 1 | 0.8 | Brownfield. Part of allocation HW4 in HWAAP (for rest of allocation see below in residual allocations). Reserved Matters application approved Jun 2017 for 74 units and development commenced on site summer 17. Estimated. | Yes | Yes | Yes | 0 | 74 | 74 | 74 | 0 | 0 | 74 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74
1301274FUL | Full | Sawtry | Sawtry |  | Church Meadows, West of St Andrew's Way, Sawtry | 2.8 | 1.4 | 17/18 completions exceeded trajectory by 10 so 18/19 projection reduced by 10. Greenfield. Site commenced summer 2017. Agent considers the site could accommodate 54 dwellings and submitted an application to increase capacity by 11 dwellings in Apr 17 (17/00927/FUL). Capacity kept at 43 dwellings in trajectory to reflect draft Local Plan allocation and permitted scheme. | Yes | Yes | Yes | 18 | 25 | 43 | 25 | 8 | 18 | 19 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
Total of small sites | Full or Reserved Matters under construction | n/a |  |  | n/a | n/a | n/a | A total of 129 completions were achieved in 17/18. These have been ascribed to 75 completions of those already under construction as at 1st April 2017 and 54 completions on those with full or reserved matters but not started. No discount applied as sites which are already started are expected to be delivered | Yes | Yes | Yes | n/a | 76 | 151 | 76 | 75 | 75 | 218 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76
Total of small sites | Full or Reserved Matters not started | n/a |  |  | n/a | n/a | n/a | A total of 129 completions were achieved in 17/18. These have been ascribed to 75 completions of those already under construction as at 1st April 2017 and 54 completions on those with full or reserved matters but not started. 138 had been predicted therefore the remaining 9 have been added to the trajectory. A 10% discount has been applied to the total of sites not yet started to allow for some sites which may not be developed | Yes | Yes | Yes | n/a | 199 | 253 | 199 | 63 | 54 |  | 63 | 63 | 64 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199
Total of small sites | Outline | n/a |  |  | n/a | n/a | n/a | Figures maintained but deferred a year as completions cannot be completed on outlines in year one. A 10% discount has been applied to the total of sites not yet started to allow for some sites which may not be developed | Yes | Yes | Yes | n/a | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 15 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
Totals | [11 empty] | Subtotal | 605 | 2536 | 605 | 371 | 374 | 410 | 329 | 153 | 104 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605
Existing Planning Permissions - Proposed Allocations
1201158OUT | Part Reserved Matters/ Part Outline | The Stukeleys/Alconbury | Alconbury And The Stukeleys | SEL1.1 | Alconbury Weald | 575 | 200 | 17/18 actual completions exceeded trajectory by 13 so 13 have been removed from 18/19 projection. Brownfield. Site progressing well. Developer says the increased level of Reserved Matters approvals and the delivery of site-wide infrastructure will ensure continued delivery. The agent considers the site could accommodate an additional 1500 dwellings, a proportion of which could realistically be developed in the next 5 years, however these dwellings are not included in the trajectory at this stage. | Yes | Yes | Yes | 163 | 4837 | 5000 | 1222 | 102 | 115 | 60 | 207 | 260 | 260 | 245 | 250 | 250 | 250 | 250 | 250 | 250 | 300 | 300 | 300 | 300 | 300 | 300 | 285 | 280 | 4837
17/01597/FUL | Full | Huntingdon | Huntingdon West | HU2 | Former Forensic Science Laboratory, Hinchingbrooke Park | 2.7 | 1.5 | Brownfield. Approved November 17. Developer says there are no constraints on delivery. | Yes | Yes | Yes | 0 | 103 | 103 | 103 | 0 | 0 | 0 | 30 | 60 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103
16/00194/OUT | Outline | Brampton | Brampton | HU12 | North West End Of Dorling Way, Brampton | 12 | 7.6 | Greenfield. Developer does not anticipate any constraints that would delay development. Reserved matters application submitted Sep 17 for 150 dwellings. | Yes | Yes | Yes | 0 | 150 | 150 | 150 | 0 | 0 | 0 | 9 | 51 | 64 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150
15/00368/OUT & 15/00643/OUT | Reserved Matters | Brampton | Brampton | HU13 | Brampton Park (formerly RAF Brampton) | 29 | 12 | 17/18 completions exceeded trajectory by 44 so 21/22 and 22/23 projections amended reflecting agents comment on delivery timescale. Brownfield. Site is progressing well. Agent says that the number of housebuilders on site means the bulk of delivery will be in the next 2-3 years. | Yes | Yes | Yes | 96 | 507 | 603 | 507 | 52 | 96 | 243 | 224 | 117 | 84 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 507
16/01484/OUT | Outline | Brampton | Brampton | HU14 | Brampton Park Golf Club | 3 | 1.5 | Greenfield. Agent says site could accommodate 68 dwellings and foresees no constraints on development. Capacity kept at 65 in line with draft Local Plan allocation. Application submitted for 68 dwellings Sep 17 (17/01959/FUL). | Yes | Yes | Yes | 0 | 65 | 65 | 65 | 0 | 0 | 0 | 49 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
16/01477/FUL | Full | Godmanchester | Godmanchester | HU18 | Wigmore Farm Buildings, Silver St, Godmanchester | 0.7 | 0.5 | Greenfield. Approved August 2017. Developer's website shows homes as 'coming soon'. Estimated | Yes | Yes | Yes | 0 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
1200685OUT | Part Reserved Matters/ Part Outline | Godmanchester | Godmanchester | HU19 | Bearscroft Farm, Godmanchester | 41.8 | 25 | 18/19 trajectory increased by 2 to account for under delivery in 17/18. Greenfield. Site progressing well. | Yes | Yes | Yes | 179 | 573 | 753 | 477 | 95 | 93 | 90 | 97 | 95 | 95 | 95 | 95 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573
0900411FUL | Full | St Neots | St Neots Priory Park | SN1 | Windmill Row, St Neots | 0.4 | 0.4 | Updated to reflect current situation as discussed in Matter 8 hearing session. Brownfield. Site in multiple ownership. Allocated in Local Plan Alteration 2002. Included in St Mary's Urban Village Framework & Masterplan 2006. 24 units permitted on part (0900411FUL) Dec 14. 17/02257/NMA was permitted Nov 17 for an amendment to the approved application, and the agent has indicated that the applicants intend to commence development in December 17. See SN6 in Draft Local Plan sites below for draft Local Plan allocation which will be 40 dwellings in total on a larger site than original 2002 allocation. No response from agents so estimated. Application submitted for change of use of the chapel on part of site to 2 dwellings (17/01446/FUL). | Yes | Yes | Yes | 0 | 24 | 24 | 24 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
1300389OUT | Outline | St Neots | St Neots Priory Park | SN2 | Loves Farm Reserved Site (At junction of Dramsell Rise & Cambridge Rd), St Neots | 1 | 1 | Greenfield. Agent's projections deferred by one year as a Reserved Matters application is yet to be submitted. | Yes | Yes | Yes | 0 | 41 | 41 | 41 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41
1402210OUT | Outline | Houghton & Wyton | The Hemingfords | SI1 | St Ives West - Houghton Grange, St Ives | 10.4 | 4.4 | Brownfield. See extant permissions on unallocated sites and draft allocations below for remainder of St Ives West area. The site is in the control of the Homes and Communities Agency who says technical reports and surveys are currently being undertaken. HCA's projections deferred by 2 years as appear optimistic. | Yes | Yes | Yes | 0 | 90 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
1301895OUT | Full (part) | St Ives | St Ives South | SI1 | St Ives West - The Spires (Former St Ives Golf Course) | 15.1 | 6 | 18/19 trajectory increased by 11 to account for under delivery in 17/18. Greenfield. Hybrid application for 125 dwellings in outline and 59 in full (phase 1 which is progressing well). Estimated. Application submitted Nov 17 for an extra 2 dwellings on site (17/02325/FUL) | Yes | Yes | Yes | 48 | 136 | 184 | 136 | 41 | 30 | 0 | 36 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136
1101894REM | Reserved Matters | Ramsey | Ramsey | RA1 | Ramsey Gateway, High Lode | 4.2 | 2.5 | Part brownfield. Agent says site will be commenced within 5 years. Agent's projections appear somewhat protracted, and the Council considers the site could be delivered quicker with higher annual completion rates. In light of ongoing viability work, the agent has moved delivery back by a year since the August 17 update. | Yes | Yes | Yes | 0 | 110 | 110 | 30 | 0 | 0 | 0 | 0 | 5 | 5 | 10 | 10 | 10 | 15 | 15 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110
16/02379/REM | Reserved Matters | Ramsey | Ramsey | RA4 | Field Road, Ramsey | 5.2 | 2.6 | Greenfield. Reserved Matters application approved May 17. Estimated. Housebuilder's website states homes are 'coming soon'. | Yes | Yes | Yes | 0 | 90 | 90 | 90 | 0 | 0 | 4 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
1201274OUT | Outline | Upwood & The Raveleys | Warboys And Bury | RA8 | RAF Upwood & Upwood Hill House | 15.3 | 8 | Brownfield. Outline application approved June 17. Estimated. | Yes | Yes | Yes | 0 | 450 | 450 | 180 | 0 | 0 | 0 | 0 | 0 | 20 | 70 | 90 | 90 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450
16/01206/FUL | Full | Fenstanton | Fenstanton | FS1 | Crown Place (former Dairy Crest), Fenstanton | 3.2 | 2.2 | Brownfield. Planning application approved May 17 for 88 dwellings. Under construction September 17. | Yes | Yes | Yes | 0 | 88 | 88 | 88 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88
16/00582/FUL | Full | Fenstanton | Fenstanton | FS2 | Cambridge Road, Fenstanton - West (South of Oaklands) | 4 | 3 | Greenfield. Site commenced Dec 17. | Yes | Yes | Yes | 0 | 86 | 86 | 86 | 0 | 0 | 4 | 20 | 40 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86
16/01109/REM | Reserved Matters | Sawtry | Sawtry | SY1 | East of Glebe Farm, Sawtry | 3.8 | 2 | Greenfield. Reserved Matters application for 80 dwellings allowed on appeal April 17. Estimated. Housebuilder's website states homes are 'coming soon'. | Yes | Yes | Yes | 0 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
15/00917/OUT | Outline | Somersham | Somersham | SM2 | Newlands, Somersham | 2.5 | 0.8 | Greenfield. Application for 45 dwellings and a residential care home approved Nov 17. Estimated. | Yes | Yes | Yes | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
1401887OUT | Outline | Warboys | Warboys And Bury | WB4 | South of Farrier's Way, Warboys | 3.6 | 2.3 | Greenfield. Site spread over 2 years rather than one as suggested by agent. | Yes | Yes | Yes | 0 | 74 | 74 | 74 | 0 | 0 | 0 | 24 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74
16/02519/OUT | Outline | Warboys | Warboys and Bury | WB5 | Extension to W of Station Rd, Warboys | 3.7 | 2.4 | Greenfield. Outline application approved Oct 17. Agent says there are no constraints on delivery. | Yes | Yes | Yes | 0 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 20 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
1401547OUT | Outline | Yaxley | Yaxley And Farcet | YX1 | Askews Lane, Yaxley | 1.2 | 0.5 | Part brownfield. Agent says the site is in the final stages of being sold to a developer. Agent's projections deferred 3 years as appear optimistic given a Reserved Matters application is yet to be submitted. | Yes | Yes | Yes | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
16/00576/OUT | Outline | Buckden | Buckden | BU2 | Land off Lucks Lane And W. & S. of The Osiers & Springfield Close, Buckden | 9.7 | 5.6 | Greenfield. Allowed on appeal July 17. Agent says site is being marketed Nov 17. Reserved Matters application anticipated Aug 18, with preliminary site works Apr 19, and first completions Oct 19. | Yes | Yes | Yes | 0 | 180 | 180 | 153 | 0 | 0 | 0 | 0 | 18 | 45 | 45 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180
Totals | [11 empty] | Subtotal | 7832 | 8319 | 3744 | 290 | 334 | 425 | 720 | 965 | 851 | 653 | 555 | 473 | 355 | 355 | 270 | 270 | 300 | 300 | 300 | 300 | 300 | 300 | 285 | 280 | 7832
Existing Planning Permissions - Proposed Allocations Subject to S106
0901288OUT | Planning application approved subject to signing of S106 | St Neots | St Neots Eynesbury | SN4 | Cromwell Rd Car Park, St Neots | 0.6 | 0.5 | Deferred by 2 years as discussed in the Matter 7 hearing session as a result of progress on S106. Brownfield. Approved subject to S106 completion. Estimated. | Yes | Yes | Yes | 0 | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
Totals | [11 empty] | Subtotal | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
Total Existing Planning Permissions | [12 empty] | 8458
Other Commitments: Subject to S106
15/00486/FUL | Planning application submitted | Huntingdon | Huntingdon West |  | Hinchingbrooke Health Campus - Hinchingbrooke Nursery | 2.3 | 1.5 | Brownfield. Public sector land. 45 dwellings approved by DM Panel subject to S106 agreement May 16, however no capacity shown in trajectory due to current uncertainty over availability. | Uncertain | Yes | Uncertain | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [11 empty] | Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposed Site Allocations without Planning Permission
| Draft Local Plan allocation | The Stukeleys | Alconbury And The Stukeleys | SEL 1.2 | RAF Alconbury | 84 | 42 | Brownfield. Total capacity of the site is 1,680 dwellings. Estimated based on officer knowledge of likely timeframe for the site to be vacated. As the timeframe for vacating RAF Alconbury has been delayed by 2 years in recent months, the projections have been deferred accordingly, which means 360 dwellings are now anticipated to be delivered post 2036. | Yes | Yes | Yes | 0 | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 180 | 185 | 185 | 180 | 180 | 180 | 180 | 1320
1001712OUT | Planning application submitted | Huntingdon | Huntingdon West | HU1 | Ermine Street (South), Huntingdon | 54 | 23.1 | This relates to the part of the site south of Ermine St which was allocated in Local Plan Alteration 2002 (for remainder north of Ermine St see Draft Local Plan allocations below). Greenfield. Agent's projections deferred by 3 years given the transport mitigation required in advance of development. | Yes | Yes | Yes | 0 | 1040 | 1040 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 40 | 0 | 0 | 1040
| Draft Local Plan allocation | The Stukeleys | Alconbury And The Stukeleys | HU1 | Ermine Street (North), Huntingdon | 33 | 14 | Greenfield. This relates to the part of the site north of Ermine St (for remainder south of Ermine St see Residual Allocations above). Outline application approved Nov 15 (1300730OUT) for business park. Estimated. | Yes | Yes | Yes | 0 | 400 | 400 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400
| Draft Local Plan allocation | Huntingdon | Huntingdon West | HU3 | Former Police HQ site, Hinchingbrooke Park Road, Huntingdon | 6 | 4 | Greenfield. Public sector land. Suitable for mixed use development. Agent says the site could be deliverable within 1-3 years. The opportunity to access directly onto the proposed access road connecting the realigned A14 to Hinchingbrooke Park Road is not expected to be completed until late 2021, and would therefore delay development, so the agent's projections have been deferred. Capacity has been reduced to 75 in line with the draft Local Plan allocation. | Yes | Yes | Yes | 0 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 40 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75
HWAAP HW4 | Allocation only | Huntingdon | Huntingdon West | HU6 | George St | 3.5 | 2 | Amended to reflect planning applications as discussed at Matter 6 hearing sessions. Brownfield. Part of residue of HW4 in HWAAP (for committed sites on HW4 see above). Draft allocation in Local Plan to 2036. A planning application was submitted in Apr 17 for a housing-led mixed use development including 309 dwellings (17/00733/FUL). Agent says the site could have a capacity of up to 350 dwellings, but kept at 300 to reflect the draft Local Plan allocation. | Yes | Yes | Yes | 0 | 345 | 345 | 156 | 0 | 0 | 0 | 0 | 0 | 30 | 63 | 63 | 63 | 63 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345
16/02093/FUL | Planning application submitted | Huntingdon | Huntingdon West | HU7 | Gas Depot, Mill Common, Huntingdon | 0.6 | 0.5 | Deferred by 1 year as discussed in the Matter 6 hearing session. Brownfield. Agent says site can be delivered within 5 years. | Yes | Yes | Yes | 0 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
17/02123/OUT | Draft Local Plan allocation | Huntingdon | Huntingdon East | HU8 | Land south of Colebrook Road (California Road) Huntingdon | 1.1 | 0.8 | Deferred by 1 year as discussed in the Matter 6 hearing session. Greenfield. Application submitted for 57 units Oct 17 (17/02123/OUT). | Yes | Yes | Yes | 0 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 18 | 25 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
| Draft Local Plan allocation | Huntingdon | Huntingdon East | HU9 | Main Street, Huntingdon | 1.2 | 0.8 | Deleted as discussed in the Matter 6 hearing session. Greenfield. Agent says landowners are preparing for the marketing of the site. Estimated. | Yes | Yes | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16/00906/FUL | Planning application submitted | Godmanchester | Godmanchester | HU16 | Tyrell's Marina, Huntingdon | 0.3 | 0.3 | Brownfield. Planning application submitted May 16 for 16 dwellings as part of a mixed-use development - loss of 2 existing flats so 14 net additional. Given the significance of the flood risk any capacity for residential uses is likely to be very limited without suitable mitigation. No capacity has therefore been suggested here, although the Council would support a suitable scheme. | Yes | Yes | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Draft Local Plan allocation | Godmanchester | Godmanchester | HU17 | RGE Engineering, Godmanchester | 3.8 | 1.8 | Brownfield. Agent considers site could accommodate up to 150 dwellings and be delivered within 5 years. Capacity kept in line with draft Local Plan allocation, and deferred as no planning application has yet been submitted, and the existing business has to be relocated . | Yes | Yes | Yes | 0 | 90 | 90 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
1300388OUT | Planning application submitted | St Neots | St Neots Priory Park | SEL 2 | St Neots East - Loves Farm East | 71.5 | 60 | Adjusted to reflect Gallagher's written statement as discussed at the Matter 6 hearing session. Greenfield. 1300388OUT submitted for mixed uses including 1020 dwellings. | Yes | Yes | Yes | 0 | 1020 | 1020 | 330 | 0 | 0 | 0 | 0 | 0 | 30 | 115 | 185 | 185 | 185 | 115 | 115 | 65 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020
17/02308/OUT | Draft Local Plan allocation | St Neots | St Neots Priory Park | SEL 2 | St Neots East - Wintringham Park | 59.6 | 50 | Adjusted to reflect Urban and Civic's written statement as discussed at the Matter 6 hearing session. Greenfield. Hybrid planning application submitted Nov 17 for up to 2800 dwellings as part of a mixed use development (17/02308/OUT) | Yes | Yes | Yes | 0 | 2800 | 2800 | 665 | 0 | 0 | 0 | 0 | 65 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 135 | 0 | 0 | 2800
| Draft Local Plan allocation | St Neots | St Neots Priory Park | SN1 | St Mary's Urban Village, St Neots | 0.4 | 0.4 | Updated to reflect Brook House position as discussed in the Matter 7 hearing session. Brownfield. See Windmill Row in extant planning permissions on allocated sites above for rest of site with planning permission. Included in St Mary's Urban Village Framework & Masterplan 2006. Draft Local Plan allocation will be wider area than 2002 allocation. 3 dwellings permitted May 14 on part of site (1301969FUL) which commenced summer 2016. Estimated. | Yes | Yes | Yes | 3 | 18 | 21 | 18 | 3 | 3 | 0 | 0 | 0 | 8 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
| Draft Local Plan allocation | St Neots | St Neots Eynesbury | SN3 | Cromwell Road North, St Neots | 2.6 | 1 | Mixed green/brown. Agents considers site could accommodate up to 120 dwellings, however the capacity has been kept at 80 to reflect the draft Local Plan allocation that takes account of constraints imposed by the existing culvert and the EA's request to open this up. A higher density could potentially be achieved if the culvert is retained. | Yes | Yes | Yes | 0 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80
15/00634/FUL | Planning application submitted | St Neots | St Neots Priory Park | SN5 | Former Youth Centre, Priory Rd, St Neots | 0.5 | 0.4 | Brownfield. Application submitted Apr 2015 for 14 dwellings. Given the significance of the flood risk, any capacity for residential uses is likely to be very limited without suitable mitigation. No capacity has therefore been suggested here, although the Council would support a suitable scheme. | Yes | Yes | Yes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Draft Local Plan allocation | Little Paxton | Little Paxton | SN6 | North of St James Road to North of High Street, Little Paxton | 4.7 | 3.5 | Greenfield. Agent says the site is available and could readily be delivered within 5 years. The landowner intends to commence gathering of baseline evidence in advance of submission of a planning application. However, the site has extant consent for mineral extraction until the mid 2020s, so the agent's projections have been deferred. | Yes | Yes | Yes | 0 | 35 | 35 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
1201890 & 1201891FUL | Planning applications submitted | St Ives | St Ives South | SI1 | St Ives West - north & east of The How | 2.7 | 1.3 | Greenfield. See Houghton Grange in Residual Allocated Sites and The Spires in Extant Permissions on Unallocated Sites above for the remainder of the St Ives West area. Approved subject to satisfactory completion of a S106 Apr 17. Agent says site could be completed by end 2018. | Yes | Yes | Yes | 0 | 7 | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
1301056OUT | Planning application submitted | Houghton & Wyton | The Hemingfords | SI1 | St Ives West - Land Between Houghton Grange & The How | 18.7 | 7 | Greenfield. See Houghton Grange in Residual Allocated Sites and The Spires in Extant Permissions on Unallocated Sites above for the remainder of the St Ives West area. The field is currently let on a Farm Business Tenancy, due to terminate end March 2019. The Homes and Community Agency act for the site, and say it could accommodate 224 dwellings, however the capacity has been kept at 125 in line with the draft local Plan allocation, and reflecting the draft built-up area and anti-coalescence policies in the Houghton & Wyton Neighbourhood Plan. | Yes | Yes | Yes | 0 | 125 | 125 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125
16/01485/OUT | Planning application submitted | St Ives | St Ives South | SI2 | St Ives Football Club | 1.3 | 1.3 | Greenfield. Outline application submitted Aug 2016 for 30 dwellings. Development dependent on successful relocation of Football Club (for which permission was granted Oct 15). Agent says site will become available for development from 2020 when relocation of football club can commence. | Yes | Yes | Yes | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
| Draft Local Plan allocation | St Ives | St Ives South | SI4 | Former Car Showroom, London Rd | 1.2 | 0.6 | Deferred by 1 year to reflect Matter 8 hearing session. Brownfield. Agent considers the site capacity could be up to 75 dwellings, but kept at 50 to reflect draft Local Plan allocation. Planning application in preparation. | Yes | Yes | Yes | 0 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
16/00311/FUL | Planning application submitted | Ramsey | Ramsey | RA2 | Ramsey Gateway (Land Adjacent St Marys Road Industrial Estate) | 2 | 1.3 | Brownfield. Application for 52 dwellings submitted Feb 16. Agent says there are no constraints to development, and the site can be delivered within 5 years. Will be developed simultaneously with 94 Great Whyte as the sites have interlinked public open space provision. | Yes | Yes | Yes | 0 | 52 | 52 | 52 | 0 | 0 | 0 | 0 | 0 | 20 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
| Draft Local Plan allocation | Ramsey | Ramsey | RA3 | West Station Yard & Northern Mill | 0.8 | 0.6 | Brownfield. Site being actively marketed. Potential to benefit from the proposed Cambs & Peterborough Combined Authority Regeneration Strategy for Ramsey. Estimated. | Yes | Yes | Yes | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 30
LPA site19 | Allocation only | Ramsey | Ramsey | RA5 | Whytefield Rd, Ramsey | 0.9 | 0.8 | Brownfield. Allocation in Local Plan Alteration 2002. Land in multi ownership, however an agent is now acting for all the landowners with a view to submitting a planning application in the near future. Estimated. | Yes | Yes | Yes | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
15/02384/FUL | Planning application submitted | Ramsey | Ramsey | RA6 | 94 Great Whyte, Ramsey | 0.7 | 0.4 | Brownfield. Application for 32 dwellings submitted Dec 15. Agent says the site can be delivered within 5 years. Will be developed simultaneously with Ramsey Gateway (Land Adjacent St Marys Road Industrial Estate) as the sites have interlinked public open space provision. They anticipate this smaller site would be completed first. | Yes | Yes | Yes | 0 | 32 | 32 | 32 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
| Draft Local Plan allocation | Bury | Warboys and Bury | RA7 | East of Valiant Square, Bury | 3.6 | 2.5 | Deferred by 2 years to reflect progress on site as discussed at the Matter 9 hearing session. Greenfield. Agent anticipates planning application being submitted and approved by late 2018, with development commencing early/mid 2019. | Yes | Yes | Yes | 0 | 90 | 90 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 30 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
| Draft Local Plan allocation | Buckden | Buckden | BU1 | East of Silver Street and South of A1, Buckden | 14.8 | 7.4 | Greenfield. Agent considers site could accommodate up to 330 dwellings. Capacity kept at 270 to reflect draft Local Plan allocation and deferred by 2 years. | Yes | Yes | Yes | 0 | 270 | 270 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 69 | 69 | 69 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270
| Draft Local Plan allocation | Fenstanton | Fenstanton | FS3 | Cambridge Road, Fenstanton - East | 2.4 | 1.6 | Greenfield. Agent says site could accommodate 47 dwellings, however the capacity has been kept at 35 to match the draft Local Plan allocation. | Yes | Yes | Yes | 0 | 35 | 35 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
| Draft Local Plan allocation | Kimbolton | Kimbolton and Staughton | KB1 | West of Station Road, Kimbolton | 1.5 | 0.7 | Amended to reflect planning application as noted at the Matter 10 hearing session. Greenfield. Agent says site could accommodate up to 25 dwellings. Capacity of 23 dwellings reflects recent discussions with the agent on a potential scheme, which could be delivered within 5 years. | Yes | Yes | Yes | 0 | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 10 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
| Draft Local Plan allocation | Kimbolton | Kimbolton and Staughton | KB2 | North of Station Road/Stow Road, Kimbolton | 2.5 | 1.9 | Greenfield. Agent's projections deferred by 1 year as no planning application has been submitted. | Yes | Yes | Yes | 0 | 65 | 65 | 65 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65
17/00077/OUT | Planning application submitted | Sawtry | Sawtry | SY2 | South of Gidding Rd, Sawtry | 10.8 | 7 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 295 | 295 | 225 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295
| Draft Local Plan allocation | Somersham | Somersham | SM1 | College Farm, West of Newlands Industrial Estate, Somersham | 1.8 | 1.6 | Greenfield. Agent says site is currently available for development and could be delivered within 5 years. | Yes | Yes | Yes | 0 | 55 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 30 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55
| Draft Local Plan allocation | Somersham | Somersham | SM3 | The Pasture, Somersham | 0.9 | 0.3 | Greenfield. The agent considers the site could accommodate 20 dwellings. Capacity kept at 15 to reflect draft Local Plan allocation and deferred as no planning application has been submitted. | Yes | Yes | Yes | 0 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
| Draft Local Plan allocation | Somersham | Somersham | SM4 | Somersham Town Football Club and Pond Closes, Somersham | 3.8 | 1.2 | Greenfield. Agent says there are no constraints on delivery, and the site could be delivered within 5 years - cautious approach taken and only 25 dwellings included in first 5 years. | Yes | Yes | Yes | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
| Draft Local Plan allocation | Somersham | Somersham | SM5 | East of Robert Avenue, Somersham | 2.8 | 2.1 | Delete due to access as discussed in the matter 10 hearing session. Greenfield. Agent says the site is available and can realistically be developed within 5 years. Agent's projections deferred by 2 years and spread over 2 years rather than one. | Yes | Yes | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Draft Local Plan allocation | Somersham | Somersham | SM6 | North of The Bank, Somersham | 2.1 | 1.2 | Defer by 2 years snd split 40 dwellings per year as discussed in the Matter 10 hearing session. Greenfield. Site's owner says it could realistically be delivered within 5 years. Their projections deferred by one year as appear optimistic given no planning application has yet been submitted. | Yes | Yes | Yes | 0 | 120 | 120 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120
| Draft Local Plan allocation | Warboys | Warboys and Bury | WB1 | West of Ramsey Road, Warboys | 1.7 | 1.1 | Amended to reflect agents comments as discussed at the Matter 10 hearing session. Greenfield. Site in dual ownership. Both agents responded with slightly different timeframes- deferred projections by 2 years as appear optimistic given no planning application has been submitted, although it is understood appraisal work is being carried out on part of the site. | Yes | Yes | Yes | 0 | 45 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 20 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45
| Draft Local Plan allocation | Warboys | Warboys and Bury | WB2 | Manor Farm Buildings, Warboys | 0.6 | 0.3 | Defer all dwellings to 2021/2022. Greenfield. Agent says the owner is actively seeking to relocate the current farmyard use. Lead-in time could be reduced if a temporary location is found. | Yes | Yes | Yes | 0 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
| Draft Local Plan allocation | Warboys | Warboys and Bury | WB3 | South of Stirling Close, Warboys | 3.8 | 1.3 | Greenfield. Agent's projections deferred by 1 year as no planning application has been submitted. | Yes | Yes | Yes | 0 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 15 | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50
| Draft Local Plan allocation | Alconbury | Alconbury And The Stukeleys | AL1 | North of School Lane, Alconbury | 6.3 | 3.1 | Greenfield. Agent considers site could accommodate 110-130 dwellings. Capacity kept at 95 to reflect draft Local Plan allocation. | Yes | Yes | Yes | 0 | 95 | 95 | 95 | 0 | 0 | 0 | 0 | 0 | 15 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95
17/00906/OUT | Planning application submitted | Colne | Earith | BL1 | Land West of Longacres, Bluntisham | 7.8 | 4.3 | Defered by 1 year as discussed at the Matter 11 hearing session. Greenfield. Agent says site is achievable within 5 years. Planning application submitted April 17 for up to 135 dwellings. | Yes | Yes | Yes | 0 | 135 | 135 | 135 | 0 | 0 | 0 | 0 | 0 | 35 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135
17/01015/OUT | Planning application submitted | Bluntisham | Earith | BL2 | North of 10 Station Road, Bluntisham | 1.1 | 0.8 | Greenfield. Agent says site can be made immediately available and could be developed over 2 years. Planning application submitted May 17 for residential and commercial development (30 dwellings and 4 replacement commercial units). Agent's projections deferred by one year. | Yes | Yes | Yes | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30
| Draft Local Plan allocation | Great Staughton | Kimbolton and Staughton | GS1 | South of 29 The Green, Great Staughton | 0.7 | 0.6 | Greenfield. Agent says there are no constraints on delivery. Agent's projections deferred one year as appear optimistic given no planning application has yet been submitted. | Yes | Yes | Yes | 0 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
| Draft Local Plan allocation | Great Staughton | Kimbolton And Staughton | GS2 | Between 20 Cage Lane and Averyhill, Great Staughton | 0.4 | 0.4 | Greenfield. Owner says site is immediately available, and could be developed within 5 years. | Yes | Yes | Yes | 0 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
Totals | [11 empty] | Subtotal | 9065 | 9068 | 2840 | 3 | 3 | 0 | 7 | 130 | 607 | 992 | 1104 | 925 | 772 | 600 | 513 | 365 | 375 | 480 | 500 | 500 | 480 | 355 | 180 | 180 | 9065
Other Sources - 'Prior Approval' Conversions to C3 residential use under GPDO
15/02304/P3JPA | Prior approval not required | St Ives | St Ives South |  | 2 The Meadow, St Ives | 0.02 | 0.02 | Brownfield. (note completed May 17) | Yes | Yes | Yes | 10 | 0 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16/02593/P3JPA | Prior approval not required | St Ives | St Ives South |  | 8 The Meadow, St Ives | 0.02 | 0.02 | Brownfield. Estimated. | Yes | Yes | Yes | 0 | 14 | 14 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
17/00168/P3JPA | Prior approval not required | St Neots | St Neots Priory Park |  | 1A South Street, St Neots | 0.03 | 0.03 | Brownfield. Agent says site will be completing within a year. | Yes | Yes | Yes | 0 | 12 | 12 | 12 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
16/00495/P3JPA | Prior approval not required | St Neots | St Neots Priory Park |  | 5 Station Road, St Neots | 0.1 | 0.1 | Brownfield. Estimated. | Yes | Yes | Yes | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
15/00147/PMBPA | Prior approval not required | Pidley-cum-Fenton | Somersham |  | Avenue Farm, Fenton | 0.03 | 0.03 | Greenfield. Last unit under construction | Yes | Yes | Yes | 3 | 0 | 3 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1400897PACOU | Prior approval not required | Pidley-cum-Fenton | Somersham |  | Unit 5 Fen Rd Industrial Estate, Pidley | 0.01 | 0.01 | 18/19 trajectory increased by 2 to account for under delivery in 17/18. Brownfield. Remaining 2 units under construction | Yes | Yes | Yes | 1 | 2 | 3 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
14/01702/PMBPA | Prior approval not required | Houghton and Wyton | The Hemingfords |  | Adj Manor Farm, Wyton | 0.08 | 0.08 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
14/02026/PMBPA | Prior approval not required | Ramsey | Ramsey |  | Dentons Farm, Ramsey St Marys | 0.24 | 0.03 | 17/18 completions exceeded trajectory by 2 so 18/19 reduced to zero as site is complete. Greenfield. Estimated. | Yes | Yes | Yes | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/00248/P3JPA | Prior approval not required | St Ives | St Ives South |  | 1 The Quay, St Ives | 0.01 | 0.01 | 17/18 completions exceeded trajectory by 2 so 18/19 reduced to zero as site is complete. Brownfield. Estimated. | Yes | Yes | Yes | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/00342/PMBPA | Prior approval not required | Warboys | Warboys And Bury |  | Wilsons Orchard, Warboys | 0.08 | 0.03 | 18/19 trajectory increased by 1 to account for under delivery in 17/18. Greenfield. Under construction | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15/00727/PMBPA | Prior approval not required | Farcet | Yaxley And Farcet |  | SW of Cosa Mia, Farcet | 0.02 | 0.01 | 18/19 trajectory increased by 1 to account for under delivery in 17/18. Greenfield. Under construction. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15/00649/P3PPA | Prior approval not required | St Neots | St Neots Eaton Socon |  | Shop, 210 Great North Rd, St Neots | 0.03 | 0.01 | Brownfield. Under construction | Yes | Yes | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/02394/P3JPA | Prior approval not required | St Neots | St Neots Eaton Socon |  | 210 Great North Rd, St Neots | 0.03 | 0.01 | 17/18 completions exceeded trajectory by 2 so 18/19 reduced to zero as site is complete. Brownfield. Estimated. | Yes | Yes | Yes | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/00602/PMBPA | Prior approval not required | Haddon | Elton And Folksworth |  | Toons Lodge Farm, Haddon | 0.02 | 0.02 | 18/19 trajectory increased by 1 to account for under delivery in 17/18. Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15/00729/PMBPA | Prior approval not required | Pidley-cum-Fenton | Somersham |  | Sidings Farm, Pidley | 0.01 | 0.01 | 18/19 trajectory increased by 3 to account for under delivery in 17/18. Greenfield. Under construction | Yes | Yes | Yes | 0 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
15/00870/PMBPA | Prior approval not required | Somersham | Somersham |  | Old Spot Farm, Somersham | 0.05 | 0.03 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15/00929/P3PPA | Prior approval not required | Somersham | Somersham |  | Unit 3 Oak Acres Farm, Somersham | 0.02 | 0.01 | 17/18 completions exceeded trajectory by 1 so 18/19 reduced to zero as site is complete. Brownfield. Estimated. | Yes | Yes | Yes | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/00913/P3JPA | Prior approval not required | Huntingdon | Huntingdon West |  | Red Lodge, Huntingdon | 0.05 | 0.02 | Brownfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15/00949/P3JPA | Prior approval not required | Ramsey | Ramsey |  | Heap Farm, Ramsey | 0.05 | 0.02 | Brownfield. Under construction. Estimated. | Yes | Yes | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01118/P3JPA | Prior approval not required | St Ives | St Ives South |  | 11 Bridge St, St Ives | 0.01 | 0.01 | 17/18 completions exceeded trajectory by 3 so 18/19 reduced to zero as site is complete. Brownfield. Estimated. | Yes | Yes | Yes | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01182/PMBPA | Prior approval not required | Pidley-cum-Fenton | Somersham |  | Wilobe Farm, Pidley | 0.08 | 0.04 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
15/01366/PMBPA | Prior approval not required | Alconbury Weston | Alconbury And The Stukeleys |  | Safefield Farm, Alconbury Weston | 0.05 | 0.01 | 17/18 completions exceeded trajectory by 1 so 18/19 reduced to zero as site is complete. Greenfield. Estimated. | Yes | Yes | Yes | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01515/PMBPA | Prior approval not required | Pidley-cum-Fenton | Somersham |  | Part Grass Farm, Pidley | 0.03 | 0.03 | 18/19 trajectory increased by 1 to account for under delivery in 17/18. Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15/01494/PMBPA | Prior approval not required | Elton | Elton And Folksworth |  | N of Tookey Lodge, Elton | 0.05 | 0.02 | Greenfield. Estimated. | Yes | Yes | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01940/P3PPA | Prior approval not required | Somersham | Somersham |  | Unit 2 Oak Acres Farm, Somersham | 0.02 | 0.01 | Greenfield. Under construction | Yes | Yes | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01923/PMBPA | Prior approval not required | Warboys | Warboys And Bury |  | Cherry Lodge, Warboys | 0.05 | 0.02 | Greenfield. Under construction | Yes | Yes | Yes | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15/01636/PMBPA | Prior approval not required | Somersham | Somersham |  | Dunkirk Farm, Somersham | 0.02 | 0.01 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
15/01951/PMBPA | Prior approval not required | Hemingford Grey | The Hemingfords |  | Long Lane Farm, Hemingford Grey | 0.07 | 0.03 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
15/01987/PMBPA | Prior approval not required | Pidley-cum-Fenton | Somersham |  | Southview Farm, Pidley | 0.1 | 0.1 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
15/01989/PMBPA | Prior approval not required | Pidley-cum-Fenton | Somersham |  | Southview Farm, Pidley | 0.08 | 0.04 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
15/02209/PMBPA | Prior approval not required | Haddon | Elton And Folksworth |  | Toons Lodge Farm, Haddon | 0.02 | 0.02 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
15/02379/PMBPA | Prior approval not required | Upwood & The Raveleys | Upwood And The Raveleys |  | Red House Farm, Gt Raveley | 0.1 | 0.05 | 17/18 completions exceeded trajectory by 1 so 18/19 reduced to 1. Greenfield. Estimated. | Yes | Yes | Yes | 1 | 1 | 2 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16/00223/PMBPA | Prior approval not required | Houghton and Wyton | The Hemingfords |  | Building East Of Gumecestre Farm, Wyton | 0.09 | 0.09 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
16/00384/PMBPA | Prior approval not required | Yaxley | Yaxley And Farcet |  | Heyes Farm, Yaxley | 0.09 | 0.09 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16/00221/PMBPA | Prior approval not required | Glatton | Sawtry |  | Glatton Lodge Farm, Glatton | 0.08 | 0.08 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16/02233/PMBPA | Prior approval not required | Ramsey | Ramsey |  | Banks Farm, Ramsey Mereside | 0.08 | 0.08 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16/00540/PMBPA | Prior approval not required | Wistow | Warboys And Bury |  | Hill Farm, Wistow | 0.09 | 0.09 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
16/01611/PMBPA | Prior approval not required | Farcet | Yaxley And Farcet |  | Marshalls Farm, Farcet | 0.05 | 0.05 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16/01696/PMBPA | Prior approval not required | Colne | Somersham |  | Oatlands, Colne | 0.04 | 0.04 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
16/01997/PMBPA | Prior approval not required | Somersham | Somersham |  | Jack's Barn, Somersham | 0.07 | 0.07 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16/01845/PMBPA | Prior approval not required | Somersham | Somersham |  | Long Lane Farm, Hemingford Grey | 0.07 | 0.07 | 17/18 completions exceeded trajectory by 1 so 18/19 reduced to 2. Greenfield. Estimated. | Yes | Yes | Yes | 1 | 2 | 3 | 2 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
16/02369/PMBPA | Prior approval not required | Woodwalton | Upwood And The Raveleys |  | Higney Grange, Woodwalton | 0.08 | 0.08 | 17/18 completions exceeded trajectory by 3 so 18/19 reduced to zero as site is complete. Greenfield. Estimated. | Yes | Yes | Yes | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16/02610/PMBPA | Prior approval not required | Ramsey | Ramsey |  | Woodlane Farm, Ramsey Forty Foot | 0.05 | 0.05 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16/02586/P3PPA | Prior approval not required | Colne | Somersham |  | Brook Farm, Colne | 0.04 | 0.04 | Brownfield. Estimated. | Yes | Yes | Yes | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
16/02592/P3JPA | Prior approval not required | Colne | Somersham |  | Brook Farm, Colne | 0.01 | 0.01 | Brownfield. Estimated. | Yes | Yes | Yes | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
16/02630/PMBPA | Prior approval not required | Woodwalton | Upwood And The Raveleys |  | Moat Farm, Woodwalton | 0.07 | 0.07 | 17/18 completions exceeded trajectory by 3 so 18/19 reduced to zero as site is complete. Greenfield. Estimated. | Yes | Yes | Yes | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16/02689/P3PPA | Prior approval not required | Bythorn & Keyston | Ellington |  | White Gates, Bythorn | 0.08 | 0.08 | Brownfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
17/00121/PMBPA | Prior approval not required | Catworth | Ellington |  | Church Farmhouse, Catworth | 0.04 | 0.04 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
17/00221/PMBPA | Prior approval not required | Old Weston | Ellington |  | Yew Trees, Old Weston | 0.01 | 0.01 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
16/02701/P3PPA | Prior approval not required | Somersham | Somersham |  | Ilala, Somersham | 0.03 | 0.03 | Brownfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
17/00074/PMBPA | Prior approval not required | Bluntisham | Earith |  | Witches Twist Chicken Farm, Bluntisham | 0.07 | 0.07 | Greenfield. Estimated. | Yes | Yes | Yes | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Totals | [11 empty] | Subtotal | 92 | 130 | 92 | 25 | 35 | 25 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92
Other Sources - Residual Allocated Sites
LPA site 31 - 2002 LP Alteration | Allocation only | Great Gidding | Sawtry |  | Church Farm/ Main St Gt Gidding | 0.9 | 0.8 | Greenfield. Not considered suitable for residential development as not consistent with settlement strategy. Site will not be carried forward as an allocation in the Local Plan to 2036. | Uncertain | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LPA site 32 - 2002 LP Alteration | Allocation only | Great Gidding | Sawtry |  | North west of Main St, Gt Gidding | 0.3 | 0.2 | Greenfield. Not considered suitable for residential development as not consistent with settlement strategy. Site will not be carried forward as an allocation in the Local Plan to 2036. | Uncertain | No | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [11 empty] | Subtotal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | [12 empty] | 17615 | 20074 | 7302 | 689 | 746 | 860 | 1148 | 1248 | 1562 | 1685 | 1659 | 1398 | 1127 | 955 | 783 | 635 | 675 | 780 | 800 | 800 | 780 | 655 | 465 | 460 | 17615
7302
Completions between 2011 - 2018 | [12 empty] | 4421
Total + completions from 2011-2017 | [12 empty] | 22036

## 5yr supply calculation
| All revisions to individual sites updated reflecting hearing sessions |  | 5YHLS at anticipated point of adoption
Applying 20% to target and shortfall
Plan Name | Local Plan Target |  | Local Plan Target
Plan Start | 2011-04-01 |  | 2011-04-01
Plan End | 2036-03-31 |  | 2036-03-31
Number of Years | 25 | Number of Years | 25
Number of Years remaining in DP | 19 | Number of Years remaining in DP | 17
Dwelling Target | 20100 | Dwelling Target | 20100
Target 2011-2017 | 4824 | Target 2011-2018 | 6432
Annualised target | 804 | Annualised target | 804
Completions since plan start date | 3675 | Completions since plan start date | 5568
Shortfall on target 2011-2018 | 1149 | Shortfall on target 2011-2018 | 864
5 year target + shortfall | 5169 | 5 year target + shortfall | 4884
5 year target + shortfall x 20% | 6202.8 | 5 year target + shortfall x 20% | 5860.8
Annual equivalent of target + shortfall x 20% | 1240.56 | Annual equivalent of target + shortfall x 20% | 1172.16
5 year supply | 6388 | 5 year supply | 7552
% achievable supply | 103% | % achievable supply | 128.9%
Equivalent years of target + shortfall + 20% | 5.1493 | Equivalent years of target + shortfall + 20% | 6.4428

## 5YHLS calculations
Data to Local Plan trajectory | Target 2011-2036 | 20100
| 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2016/17 | 2017/18 | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36
Dwellings Completed | Target 2011-2036 2011/12: 847; 20100 2012/13: 412; 20100 2013/14: 686; 20100 2014/15: 514; 20100 2015/16: 534; 20100 2016/17: 682; 20100 2017/18: 746
Projected completions | [7 empty] | 1148 | 1248 | 1562 | 1685 | 1659 | 1398 | 1127 | 955 | 783 | 635 | 675 | 780 | 800 | 800 | 780 | 655 | 465 | 460
Cumulative Completions | 847 | 1259 | 1945 | 2459 | 2993 | 3675 | 4421 | 5569 | 6817 | 8379 | 10064 | 11723 | 13121 | 14248 | 15203 | 15986 | 16621 | 17296 | 18076 | 18876 | 19676 | 20456 | 21111 | 21576 | 22036
Target | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804 | 804
Cumulative Target | 804 | 1608 | 2412 | 3216 | 4020 | 4824 | 5628 | 6432 | 7236 | 8040 | 8844 | 9648 | 10452 | 11256 | 12060 | 12864 | 13668 | 14472 | 15276 | 16080 | 16884 | 17688 | 18492 | 19296 | 20100
Monitor - No. dwellings above or below cumulative development plan target | 43 | -349 | -467 | -757 | -1027 | -1149 | -1207 | -863 | -419 | 339 | 1220 | 2075 | 2669 | 2992 | 3143 | 3122 | 2953 | 2824 | 2800 | 2796 | 2792 | 2768 | 2619 | 2280 | 1936
Number of years left in Plan(s) | 24 | 23 | 22 | 21 | 20 | 19 | 18 | 17 | 16 | 15 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0